## Backlog
Priority | Name | Time est. | Done
1 | Mock up | 4 | YES
1 | MoSCoW | 3 | YES
1 | Use cases | 2 | YES
1 | Group Contract | 9 | YES
1 | Database | 8 | YES
1 | User stories | 10 | YES
1 | Report | 80 | YES
1 | Domain model | 7 | YES
1 | Backlog | 7 | YES
1 | Database model | 12 | YES
1 | Register | 3 | YES
1 | Login | 2 | YES
1 | Get profile | 3 | YES
1 | Update profile | 3 | YES
1 | Delete profile | 2 | YES
1 | Multiple chats for one client | 2 | YES
1 | Create Chat | 3 | YES
1 | Update Chat | 3 | YES
1 | Find chat | 2 | YES
1 | Delete Chat | 2 | YES
1 | Join chat | 4 | YES
1 | Leave chat | 2 | YES
1 | Send message | 5 | YES
1 | Receive Message | 4 | YES
1 | Get messages | 3 | YES
1 | Remove your message | 2 | YES
1 | Fix problem statement | 2 | YES
1 | Plan driven vs agile | 3 | YES
1 | Dedicated client | 25 | YES
1 | Logout | 2 | YES
2 | Forgot password | 3 | YES
2 | Show message info | 3 | YES
2 | Get songs info | 4 | YES
2 | Choice of method | 4 | YES
2 | Play song | 1 | YES
2 | Save song | 1 | YES
2 | Create playlist | 3 | YES
2 | Get playlist | 1 | YES
2 | Update playlist | 2 | YES
2 | Delete playlist | 1 | YES
2 | Join as group | 9 | YES
2 | Join group | 1 | YES
2 | Leave group | 1 | YES
2 | Create group | 1 | YES
2 | Read group | 1 | YES
2 | Update group | 1 | YES
2 | Delete group | 1 | YES
2 | Chat users updated if info changed | 1 | YES
2 | Show newest chat info | 3 | YES
2 | Join as group | 9 | YES
2 | Show if someone is writing | 1 | YES
3 | Close chat if its deleted | 2 | YES
3 | Invite person to chat | 4 | YES
3 | Get notification | 3 | YES
3 | Remove notifications | 2 | YES
3 | One person can be logged in at once | 2 | YES
3 | Multiplayer game | 6 | YES
3 | Show if someone is writing | 1 | YES
3 | Show online persons | 2 | YES
3 | Web client | 30 | NO

## Sprint 0
Priority | Work | time-est. | 25.10.2017 | 26.10.2017 | 27.10.2017 | 31.10.2017 | 3.11.2017 | 6.11.2017 | Person | Role
2 | Mock up | 4 | 4 | 4 | 4 | 5 | 2 | 0 | Ralfs | Scrum master
2 | MoSCoW | 3 | 3 | 3 | 3 | 4 | 0 | 0 | Ralfs | Scrum master
1 | Use cases | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Ralfs | Scrum master
2 | Distribute use cases | 1 | 1 | 1 | 1 | 1 | 2 | 0 | Ralfs | Scrum master
3 | Read about chats | 3 | 3 | 3 | 2 | 1 | 0 | 0 | Ralfs | Scrum master
1 | Group Contract | 9 | 3 | 0 | 0 | 0 | 0 | 0 | Andrei
3 | Database table creation scripts | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Andrei
3 | Drop database script | 1 | 1 | 1 | 1 | 1 | 1 | 0 | Andrei
3 | Database trigger tests | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Andrei
3 | Database insert row scripts scripts | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Andrei
1 | User stories | 10 | 12 | 4 | 1 | 0 | 0 | 0 | Hannes | Product owner
3 | Create report structure | 3 | 3 | 3 | 3 | 3 | 2 | 0 | Hannes | Product owner
3 | Domain model explanation | 2 | 2 | 2 | 2 | 2 | 3 | 0 | Stoycho
1 | Backlog | 7 | 7 | 7 | 9 | 4 | 1 | 0 | All of us
2 | Database model | 12 | 12 | 12 | 12 | 7 | 2 | 0 | All of us
1 | Generate product idea | 10 | 6 | 2 | 0 | 0 | 0 | 0 | All of us
2 | Domain model | 7 | 7 | 7 | 7 | 8 | 5 | 0 | All of us
1 | Decide on development method | 2 | 1 | 0 | 0 | 0 | 0 | 0 | All of us
2 | Establish coding standards | 3 | 3 | 3 | 3 | 3 | 3 | 0 | All of us
2 | Agree on working conditions | 2 | 2 | 2 | 2 | 0 | 0 | 0 | All of us
|  | Deal remaining time: | 88 | 70.4 | 52.8 | 35.2 | 17.6 | 0
|  | Actual remianing time: | 79 | 63 | 59 | 47 | 28 | 0

## Sprint 1
Priority | Work | time-est. | 8.11.2017 | 9.11.2017 | 10.11.2017 | 11.11.2017 | 12.11.2017 | 13.11.2017 | 14.11.2017 | 15.11.2017 | 16.11.2017 | 17.11.2017 | 18.11.2017 | 19.11.2017 | 20.11.2017 | 21.11.2017 | Person | Role
1 | Register | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Login | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
2 | Forgot password | 3 | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Get profile | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Update profile | 3 | 3 | 4 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Delete profile | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
2 | Spike on email sending | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 2 | 0 | 0 | 0 | 0 | Andrei
1 | Multiple chats for one client | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 0 | 0 | Ralfs | Product owner
1 | Create Chat | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Update Chat | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Find chat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Delete Chat | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Join chat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Leave chat | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Send message | 5 | 7 | 6 | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Receive Message | 4 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Get messages | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
2 | Show message info | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Remove your message | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Spike on different communication protocols | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
2 | Close chat if its deleted | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | Ralfs | Product owner
1 | Spike on WCF | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
2 | Invite person to chat | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | Ralfs | Product owner
2 | Get notification | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Ralfs | Product owner
2 | Remove notifications | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
1 | Spike on binding | 6 | 6 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Product owner
2 | Get songs info | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 0 | Stoycho | Scrum master
1 | Spike on youtube | 6 | 6 | 6 | 6 | 4 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho | Scrum master
1 | Fix problem statement | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hannes
2 | Choice of method | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | Hannes
1 | Plan driven vs agile | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hannes
1 | Dedicated client | 25 | 25 | 25 | 25 | 25 | 23 | 21 | 17 | 13 | 9 | 9 | 8 | 5 | 3 | 0 | All of us
|  | Deal remaining time: | 118 | 108.9231 | 99.8462 | 90.7692 | 81.6923 | 72.6154 | 63.5385 | 54.4615 | 45.3846 | 36.3077 | 27.2308 | 18.1538 | 9.0769 | -2.8422e-14
|  | Actual remianing time: | 120 | 106 | 91 | 81 | 70 | 64 | 49 | 42 | 36 | 28 | 22 | 11 | 5 | 0

## Sprint 2
Priority | Work | time-est. | 22.11.2017 | 23.11.2017 | 24.11.2017 | 25.11.2017 | 26.11.2017 | 27.11.2017 | Person | Role
1 | Play song | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Save song | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Stoycho
1 | Create playlist | 3 | 2 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Get playlist | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Stoycho
2 | Update playlist | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Stoycho
2 | Delete playlist | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Stoycho
2 | Exception handling | 4 | 4 | 0 | 2 | 2 | 0 | 0 | Stoycho
2 | Multiplayer game | 6 | 6 | 3 | 1 | 0 | 0 | 0 | Andrei | Product owner
2 | Game debug/release mode execution error | 3 | 3 | 7 | 10 | 6 | 0 | 0 | Andrei | Product owner
1 | One person can be logged in at once | 2 | 2 | 2 | 2 | 2 | 0 | 0 | Andrei | Product owner
1 | Logout | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Andrei | Product owner
1 | Refactor database | 4 | 4 | 0 | 0 | 0 | 0 | 0 | Andrei | Product owner
2 | Exception handling | 5 | 5 | 5 | 5 | 3 | 0 | 0 | Andrei | Product owner
2 | Exception handling | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Join group | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Leave group | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Create group | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Read group | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Update group | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Hannes | Scrum master
1 | Delete group | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Hannes | Scrum master
2 | Chat users updated if user info changed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Ralfs
2 | Show if someone is writing | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Ralfs
2 | Show online persons | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Ralfs
2 | Show newest chat info | 3 | 3 | 2 | 0 | 0 | 0 | 0 | Ralfs
1 | Join as group | 9 | 9 | 9 | 8 | 0 | 0 | 0 | Ralfs
2 | burn down chart | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Ralfs
2 | Updating end expanding existing UI | 1 | 1 | 2 | 0 | 0 | 0 | 0 | Ralfs
2 | Exception handling | 4 | 4 | 4 | 3 | 0 | 0 | 0 | Ralfs
2 | Report planning | 18 | 18 | 18 | 18 | 18 | 24 | 0 | All of us together
2 | Spreading tasks | 8 | 8 | 0 | 0 | 0 | 0 | 0 | All of us together
|  | Deal remaining time: | 91 | 72.8 | 54.6 | 36.4 | 18.2 | 0
|  | Actual remianing time: | 90 | 61 | 49 | 31 | 24 | 0

## Sprint 3
Priority | Work | time-est. | 28.11.2017 | 29.11.2017 | 30.11.2017 | 1.12.2017 | 2.12.2017 | 3.12.2017 | 4.12.2017 | 5.12.2017 | Person | Role
2 | WCF hosting | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | Andrei | Scrum master
1 | Splitting report tasks | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei | Scrum master
1 | Fix update profile | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei | Scrum master
2 | Database Architecture | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | Andrei | Scrum master
2 | Epilogue | 3 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | Andrei | Scrum master
1 | Fix music player | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
1 | Optimize transactions | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
2 | Introduction | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
2 | Development Method of Choice | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
2 | Preliminary Study | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 0 | 0 | Stoycho | Product owner
2 | Types of Services | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | Stoycho | Product owner
1 | Choice of middleware | 1 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | Stoycho | Product owner
1 | Security in program | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
1 | Performance of project | 5 | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | Stoycho | Product owner
2 | Plan driven Vs. Agile Development | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Hannes
2 | Quality Assurance | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | Hannes
2 | Quality Criteria and Architecture | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Hannes
2 | Dedicated Client explanation | 2 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | Hannes
2 | Web Client explanation | 3 | 3 | 3 | 3 | 3 | 4 | 0 | 0 | 0 | Hannes
3 | Interesting bits of code | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | Hannes
1 | Signalr spike | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs
1 | test/optimize code | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | Ralfs
1 | Optimize transactions | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs
2 | Sprint sum-up | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 0 | Ralfs
2 | Concurrency in project | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | Ralfs
2 | Service’s Architecture | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | Ralfs
1 | MVC application | 25 | 25 | 34 | 30 | 27 | 25 | 21 | 17 | 15 | All of us together
1 | MVC spike | 10 | 10 | 13 | 10 | 6 | 0 | 0 | 0 | 0 | All of us together
|  | Deal remaining time: | 110 | 94.2857 | 78.5714 | 62.8571 | 47.1429 | 31.4286 | 15.7143 | 0
|  | Actual remianing time: | 108 | 107 | 89 | 62 | 46 | 35 | 24 | 18

## Sprint 4
Priority | Work | time-est. | 5.12.2017 | 6.12.2017 | 7.12.2017 | 8.12.2017 | 9.12.2017 | 10.12.2017 | 11.12.2017 | 12.12.2017 | 13.12.2017 | Person | Role | Date
1 | merging Report | 6 | 6 | 6 | 6 | 7 | 4 | 4 | 2 | 1 | 0 | Andrei
2 | Giving feedback on report | 8 | 8 | 8 | 5 | 4 | 2 | 0 | 0 | 0 | 0 | Andrei
1 | Requesting edits for report | 4 | 4 | 4 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Final touches for report | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Andrei
1 | Database isolation levels | 4 | 4 | 4 | 6 | 7 | 4 | 2 | 0 | 0 | 0 | Andrei
1 | Remove image from playlist in database | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Andrei
1 | Risk management | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Hannes | Product owner
1 | Quality assurance updates | 4 | 4 | 4 | 4 | 4 | 6 | 5 | 3 | 1 | 0 | Hannes | Product owner
1 | FURPS+ (using youtube) | 5 | 5 | 4 | 2 | 1 | 0 | 0 | 0 | 1 | 0 | Hannes | Product owner
2 | Update sprint report document | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | Ralfs | Scrum master
1 | Design class diagram | 10 | 10 | 13 | 8 | 2 | 0 | 0 | 0 | 0 | 0 | Ralfs | Scrum master
1 | On connection lost close connection | 2 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Ralfs | Scrum master
1 | Release product | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | Stoycho
2 | Fix naming of classes and methods | 4 | 4 | 4 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Fix all exceptions | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Fix UI | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Fix test | 3 | 3 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | Stoycho
1 | Finalize MVC | 20 | 20 | 16 | 15 | 13 | 10 | 7 | 5 | 3 | 1 | All of us
|  | Deal remaining time: | 86 | 75.25 | 64.5 | 53.75 | 43 | 32.25 | 21.5 | 10.75 | 0
|  | Actual remianing time: | 87 | 82 | 73 | 54 | 34 | 24 | 16 | 12 | 1
3 layer UI
use activity model layer class
make chat work on web client