## Backlog
Priority | Name | Done | Time est. | time-act. | time-est. | time-act. | date | Estimate | Actual
1 | Register | YES | 3 | 5 | 3 | 5 | 1 | 104 | 113 | 1
1 | Login | YES | 2 | 3 | 3 | 3 | 1 | 101 | 110 | 2
2 | Forgot password | YES | 3 | 3 | 6 | 6 | 1 | 97 | 105 | 3
1 | Get profile | YES | 3 | 3 | 2 | 2 | 1 | 91 | 99 | 4
1 | Update profile | YES | 3 | 2 | 3 | 3 | 2 | 86 | 95 | 5
1 | Delete profile | YES | 2 | 2 | 2 | 3 | 3 | 77 | 86 | 6
1 | Multiple chats for one client | YES | 2 | 1 | 2 | 2 | 3 | 68 | 72 | 7
1 | Create Chat | YES | 3 | 3 | 2 | 2 | 4 | 65 | 70 | 8
1 | Update Chat | YES | 3 | 3 | 4 | 4 | 4 | 53 | 59 | 9
1 | Find chat | YES | 2 | 2 | 3 | 3 | 5 | 46 | 52 | 10
1 | Delete Chat | YES | 2 | 2 | 2 | 1 | 5 | 41 | 46 | 11
1 | Join chat | YES | 4 | 4 | 4 | 4 | 6 | 34 | 40 | 12
1 | Leave chat | YES | 2 | 2 | 3 | 3 | 6 | 0 | 0 | 13
1 | Send message | YES | 5 | 4 | 2 | 2 | 6 |  |  | 14
1 | Receive Message | YES | 4 | 4 | 6 | 10 | 7 |  |  | 15
1 | Get messages | YES | 3 | 3 | 3 | 4 | 7 |  |  | 16
2 | Show message info | YES | 3 | 2 | 3 | 2 | 8 |  |  | 17
1 | Remove your message | YES | 2 | 3 | 5 | 4 | 9 |  |  | 18
2 | Show if someone is writing | YES | 1 | 1 | 4 | 4 | 9 |  |  | 19
2 | Close chat if its deleted | YES | 2 | 2 | 3 | 3 | 9 |  |  | 20
2 | Show online persons | YES | 2 | 2 | 2 | 2 | 10 |  |  | 21
2 | Show newest chat info | YES | 3 | 2 | 3 | 2 | 10 |  |  | 22
2 | Invite person to chat | YES | 4 | 4 | 2 | 3 | 10 |  |  | 23
2 | Get notification | YES | 3 | 4 | 1 | 1 | 11 |  |  | 24
2 | Remove notifications | YES | 2 | 2 | 4 | 5 | 11 |  |  | 25
1 | Spike on binding | YES | 6 | 10 | 2 | 2 | 12 |  |  | 26
2 | Get songs info | YES | 4 | 5 | 2 | 2 | 12 |  |  | 27
1 | Spike on youtube | YES | 6 | 6 | 3 | 2 | 12 |  |  | 28
1 | Fix problem statement | YES | 2 | 2 | 4 | 4 | 13 |  |  | 29
2 | Choice of method | YES | 4 | 4 | 3 | 4 | 13 |  |  | 30
1 | Plan driven vs agile | YES | 3 | 4 | 2 | 2 | 13 |  |  | 31
1 | Dedicated client | YES | 25 | 30 | 25 | 30 | 13 |  |  | 32
2 | Play song | + |  |  | 118 | 129 |  |  |  | 33
2 | Save song | + | [7 empty] | 34
2 | Update song | + | [7 empty] | 35
2 | Remove song | + | [7 empty] | 36
2 | Create playlist | + | [7 empty] | 37
2 | Read playlist | + | [7 empty] | 38
3 | Update playlist | + | [7 empty] | 39
3 | Delete playlist | + | [7 empty] | 40
4 | Sound equalizer | - | [7 empty] | 41
4 | Change time displaying | -
3 | Multiplayer game (scalable) | +
2 | Join as group | +
2 | Join group | +
2 | Leave group | +
2 | Create group | +
2 | Read group | +
2 | Update group | +
2 | Delete group | +
3 | Booking | -
2 | Web client | +
3 | News area | -

## Sprint 1
Priority | Work | time-est. | time-act. | Person | Role | time-est. | time-act. | date | Estimate | Actual
1 | Register | 3 | 5 | Andrei |  | 3 | 5 | 1 | 104 | 113 | 1
1 | Login | 2 | 3 | Andrei |  | 3 | 3 | 1 | 101 | 110 | 2
2 | Forgot password | 3 | 3 | Andrei |  | 6 | 6 | 1 | 97 | 105 | 3
1 | Get profile | 3 | 3 | Andrei |  | 2 | 2 | 1 | 91 | 99 | 4
1 | Update profile | 3 | 2 | Andrei |  | 3 | 3 | 2 | 86 | 95 | 5
1 | Delete profile | 2 | 2 | Andrei |  | 2 | 3 | 3 | 77 | 86 | 6
1 | Multiple chats for one client | 2 | 1 | Ralfs | Product owner | 2 | 2 | 3 | 68 | 72 | 7
1 | Create Chat | 3 | 3 | Ralfs | Product owner | 2 | 2 | 4 | 65 | 70 | 8
1 | Update Chat | 3 | 3 | Ralfs | Product owner | 4 | 4 | 4 | 53 | 59 | 9
1 | Find chat | 2 | 2 | Ralfs | Product owner | 3 | 3 | 5 | 46 | 52 | 10
1 | Delete Chat | 2 | 2 | Ralfs | Product owner | 2 | 1 | 5 | 41 | 46 | 11
1 | Join chat | 4 | 4 | Ralfs | Product owner | 4 | 4 | 6 | 34 | 40 | 12
1 | Leave chat | 2 | 2 | Ralfs | Product owner | 3 | 3 | 6 | 0 | 0 | 13
1 | Send message | 5 | 4 | Ralfs | Product owner | 2 | 2 | 6
1 | Receive Message | 4 | 4 | Ralfs | Product owner | 6 | 10 | 7
1 | Get messages | 3 | 3 | Ralfs | Product owner | 3 | 4 | 7
2 | Show message info | 3 | 2 | Ralfs | Product owner | 3 | 2 | 8
1 | Remove your message | 2 | 3 | Ralfs | Product owner | 5 | 4 | 9
2 | Show if someone is writing | 1 | 1 | Ralfs | Product owner | 4 | 4 | 9
2 | Close chat if its deleted | 2 | 2 | Ralfs | Product owner | 3 | 3 | 9
2 | Show online persons | 2 | 2 | Ralfs | Product owner | 2 | 2 | 10
2 | Show newest chat info | 3 | 2 | Ralfs | Product owner | 3 | 2 | 10
2 | Invite person to chat | 4 | 4 | Ralfs | Product owner | 2 | 3 | 10
2 | Get notification | 3 | 4 | Ralfs | Product owner | 1 | 1 | 11
2 | Remove notifications | 2 | 2 | Ralfs | Product owner | 4 | 5 | 11
1 | Spike on binding | 6 | 10 | Ralfs | Product owner | 2 | 2 | 12
2 | Get songs info | 4 | 5 | Stoicho | Scrum master | 2 | 2 | 12
1 | Spike on youtube | 6 | 6 | Stoicho | Scrum master | 3 | 2 | 12
1 | Fix problem statement | 2 | 2 | Hannes |  | 4 | 4 | 13
2 | Choice of method | 4 | 4 | Hannes |  | 3 | 4 | 13
1 | Plan driven vs agile | 3 | 4 | Hannes |  | 2 | 2 | 13
1 | Dedicated client | 25 | 30 | All of us |  | 25 | 30 | 13
[6 empty] | 118 | 129

## Sprint 2
Priority | Work | time-est. | time-act. | Person | Role
1 | Play song | 1 |  | Stoicho
1 | Save song | 1 |  | Stoicho
1 | Update song | 2 |  | Stoicho
1 | Remove song | 1 |  | Stoicho
1 | Create playlist | 2 |  | Stoicho
1 | Read playlist | 1 |  | Stoicho
2 | Update playlist | 2 |  | Stoicho
2 | Delete playlist | 1 |  | Stoicho
2 | Multiplayer game (scalable) | 6 |  | Andrei | Product owner
1 | Fix database | 1 | 3 | Andrei | Product owner
1 | Join as group | 1 |  | Ralfs
1 | Join group | 1 |  | Hannes | Scrum master
1 | Leave group | 1 |  | Hannes | Scrum master
1 | Create group | 1 |  | Hannes | Scrum master
1 | Read group | 1 |  | Hannes | Scrum master
1 | Update group | 1 |  | Hannes | Scrum master
1 | Delete group | 1 |  | Hannes | Scrum master
2 | Web client | 30 |  | Each of us
3 | News area
2 | exceptions | 2 | 2 | Each of us
2 | tests | 10 | 8 | Each of us
2 | db refactoring | 10 |  | Each of us
2 | burn down chart | 1 | 1 | Ralfs
2 | Message encryption | 4 |  | Ralfs
2 | Updated person updated in all chats |  |  | Ralfs