## Backlog
Priority | Name | Done | Time est. | time-act.
1 | Register | YES | 3 | 5
1 | Login | YES | 2 | 3
2 | Forgot password | YES | 3 | 3
1 | Get profile | YES | 3 | 3
1 | Update profile | YES | 3 | 2
1 | Delete profile | YES | 2 | 2
1 | Multiple chats for one client | YES | 2 | 1
1 | Create Chat | YES | 3 | 3
1 | Update Chat | YES | 3 | 3
1 | Find chat | YES | 2 | 2
1 | Delete Chat | YES | 2 | 2
1 | Join chat | YES | 4 | 4
1 | Leave chat | YES | 2 | 2
1 | Send message | YES | 5 | 4
1 | Receive Message | YES | 4 | 4
1 | Get messages | YES | 3 | 3
2 | Show message info | YES | 3 | 2
1 | Remove your message | YES | 2 | 3
2 | Show if someone is writing | YES | 1 | 1
2 | Close chat if its deleted | YES | 2 | 2
2 | Show online persons | YES | 2 | 2
2 | Show newest chat info | YES | 3 | 2
2 | Invite person to chat | YES | 4 | 4
2 | Get notification | YES | 3 | 4
2 | Remove notifications | YES | 2 | 2
1 | Spike on binding | YES | 6 | 10
2 | Get songs info | YES | 4 | 5
1 | Spike on youtube | YES | 6 | 6
1 | Fix problem statement | YES | 2 | 2
2 | Choice of method | YES | 4 | 4
1 | Plan driven vs agile | YES | 3 | 4
1 | Dedicated client | YES | 25 | 30
2 | Play song | YES | 1 | 2
2 | Save song | YES | 1 | 1
2 | Create playlist | YES | 2 | 3
2 | Get playlist | YES | 1 | 1
2 | Update playlist | YES | 2 | 2
2 | Delete playlist | YES | 1 | 1
3 | Multiplayer game | YES | 6 | 5
2 | One person can be logged in at once | YES | 2 | 2
1 | Logout | YES | 2 | 2
2 | Join as group | YES | 10 | 8
2 | Join group | YES | 1 | 1
2 | Leave group | YES | 1 | 1
2 | Create group | YES | 1 | 1
2 | Read group | YES | 1 | 1
2 | Update group | YES | 1 | 1
2 | Delete group | YES | 1 | 1
1 | Mock up | YES | 4 | 5
1 | MoSCoW | YES | 3 | 3
1 | Use cases | YES | 2 | 3
1 | Distribute usecases | YES | 1 | 2
1 | Group Contract | YES | 9 | 9
1 | Domain model | YES | 7 | 5
1 | Domain model explanation | YES | 2 | 2
1 | Database model | YES | 12 | 13
1 | Database table creation scripts | YES | 2 | 2
1 | Drop database script | YES | 1 | 1
1 | Database triger tests | YES | 2 | 2
1 | Database insert row scripts scripts | YES | 3 | 3
1 | Backlog | YES | 7 | 8
1 | User stories | YES | 10 | 11
1 | Create report structure | YES | 3 | 3
1 | Generate product idea | YES | 10 | 14
1 | Read about chats | YES | 3 | 4
1 | Decide on development method | YES | 2 | 2
1 | Establish coding standards | YES | 3 | 2
1 | Agree on working conditions | YES | 2 | 2
2 | Web client | NO
1 | Sys dev report | NO
1 | Techno/Programming report | NO

## Sprint 0
Priority | Work | time-est. | time-act. | Person | Role |  | time-est. | time-act. | date | Estimate | Actual
2 | Mock up | 4 | 5 | Ralfs | Scrum master |  | 9 | 9 | 1 | 88 | 96 | 0
2 | MoSCoW | 3 | 3 | Ralfs | Scrum master |  | 10 | 14 | 1 | 69 | 73 | 1
1 | Use cases | 2 | 3 | Ralfs | Scrum master |  | 3 | 3 | 2 | 45 | 50 | 2
2 | Distribute usecases | 1 | 2 | Ralfs | Scrum master |  | 7 | 5 | 2 | 25 | 27 | 3
1 | Group Contract | 9 | 9 | Andrei |  |  | 10 | 11 | 2 | 16 | 17 | 4
2 | Domain model | 7 | 5 | All of us |  |  | 2 | 2 | 2 | 0 | 0 | 5
3 | Domain model explanation | 2 | 2 | Stoycho |  |  | 2 | 2 | 2
2 | Database model | 12 | 13 | All of us |  |  | 2 | 3 | 3
3 | Database table creation scripts | 2 | 2 | Andrei |  |  | 4 | 5 | 3
3 | Drop database script | 1 | 1 | Andrei |  |  | 2 | 2 | 3
3 | Database triger tests | 2 | 2 | Andrei |  |  | 12 | 13 | 3
3 | Database insert row scripts scripts | 3 | 3 | Andrei |  |  | 1 | 2 | 4
1 | Backlog | 7 | 8 | All of us |  |  | 2 | 2 | 4
1 | User stories | 10 | 11 | Hannes | Product owner | Do it! | 1 | 1 | 4
3 | Create report structure | 3 | 3 | Hannes | Product owner |  | 2 | 2 | 4
1 | Generate product idea | 10 | 14 | All of us |  |  | 3 | 3 | 4
3 | Read about chats | 3 | 4 | Ralfs | Scrum master |  | 7 | 8 | 5
1 | Decide on development method | 2 | 2 | All of us |  |  | 3 | 3 | 5
2 | Establish coding standards | 3 | 2 | All of us |  |  | 3 | 4 | 5
2 | Agree on working conditions | 2 | 2 | All of us |  |  | 3 | 2 | 5
[7 empty] | 88 | 96

## Sprint 1
Priority | Work | time-est. | time-act. | Person | Role | time-est. | time-act. | date | Estimate | Actual
1 | Register | 3 | 5 | Andrei |  | 3 | 5 | 1 | 118 | 129 | 0
1 | Login | 2 | 3 | Andrei |  | 3 | 3 | 1 | 104 | 113 | 1
2 | Forgot password | 3 | 3 | Andrei |  | 6 | 6 | 1 | 101 | 110 | 2
1 | Get profile | 3 | 3 | Andrei |  | 2 | 2 | 1 | 97 | 105 | 3
1 | Update profile | 3 | 2 | Andrei |  | 3 | 3 | 2 | 91 | 99 | 4
1 | Delete profile | 2 | 2 | Andrei |  | 2 | 3 | 3 | 86 | 95 | 5
2 | Spike on email sending | 3 | 2 | Andrei |  | 2 | 2 | 3 | 77 | 86 | 6
1 | Multiple chats for one client | 2 | 1 | Ralfs | Product owner | 2 | 2 | 4 | 68 | 72 | 7
1 | Create Chat | 3 | 3 | Ralfs | Product owner | 4 | 4 | 4 | 65 | 70 | 8
1 | Update Chat | 3 | 3 | Ralfs | Product owner | 3 | 3 | 5 | 53 | 59 | 9
1 | Find chat | 2 | 2 | Ralfs | Product owner | 2 | 1 | 5 | 46 | 52 | 10
1 | Delete Chat | 2 | 2 | Ralfs | Product owner | 4 | 4 | 6 | 41 | 46 | 11
1 | Join chat | 4 | 4 | Ralfs | Product owner | 3 | 3 | 6 | 27 | 32 | 12
1 | Leave chat | 2 | 2 | Ralfs | Product owner | 2 | 2 | 6 | 0 | 0 | 13
1 | Send message | 5 | 4 | Ralfs | Product owner | 6 | 10 | 7
1 | Receive Message | 4 | 4 | Ralfs | Product owner | 3 | 4 | 7
1 | Get messages | 3 | 3 | Ralfs | Product owner | 3 | 2 | 8
2 | Show message info | 3 | 2 | Ralfs | Product owner | 5 | 4 | 9
1 | Remove your message | 2 | 3 | Ralfs | Product owner | 4 | 4 | 9
1 | Spike on different communication protocols | 1 | 1 | Ralfs | Product owner | 3 | 3 | 9
2 | Close chat if its deleted | 2 | 2 | Ralfs | Product owner | 2 | 2 | 10
1 | Spike on WCF | 2 | 2 | Ralfs | Product owner | 3 | 2 | 10
2 | Invite person to chat | 4 | 4 | Ralfs | Product owner | 2 | 3 | 10
2 | Get notification | 3 | 4 | Ralfs | Product owner | 1 | 1 | 11
2 | Remove notifications | 2 | 2 | Ralfs | Product owner | 4 | 5 | 11
1 | Spike on binding | 6 | 10 | Ralfs | Product owner | 2 | 2 | 12
2 | Get songs info | 4 | 5 | Stoycho | Scrum master | 2 | 2 | 12
1 | Spike on youtube | 6 | 6 | Stoycho | Scrum master | 3 | 2 | 12
1 | Fix problem statement | 2 | 2 | Hannes |  | 4 | 4 | 12
2 | Choice of method | 4 | 4 | Hannes |  | 3 | 4 | 12
1 | Plan driven vs agile | 3 | 4 | Hannes |  | 2 | 2 | 13
1 | Dedicated client | 25 | 30 | All of us |  | 25 | 30 | 13
[6 empty] | 118 | 129

## Sprint 2
Priority | Work | time-est. | time-act. | Person | Role | Date |  |  |  | Date |  |  | time-est. | time-act. | Date
1 | Play song | 1 | 2 | Stoycho |  | 22.11.2017 |  |  | 90 | 22.11.2017 |  |  | 90 | 90 | 22.11.2017
1 | Save song | 1 | 1 | Stoycho |  | 23.11.2017 |  |  | 18 | 23.11.2017 |  |  | 72 | 73 | 23.11.2017
1 | Create playlist | 2 | 3 | Stoycho |  | 23.11.2017 |  |  | 18 | 24.11.2017 |  |  | 54 | 57 | 24.11.2017
1 | Get playlist | 1 | 1 | Stoycho |  | 24.11.2017 |  |  | 2 | 25.11.2017 |  |  | 36 |  | 25.11.2017
2 | Update playlist | 2 | 2 | Stoycho |  | 24.11.2017 |  |  | -20 | 26.11.2017 |  |  | 18 |  | 26.11.2017
2 | Delete playlist | 1 | 1 | Stoycho |  | 23.11.2017 |  |  | -26 | 27.11.2017 |  |  | 0 |  | 27.11.2017
2 | Multiplayer game | 6 | 5 | Andrei | Product owner | 24.11.2017
2 | Game debug/release mode execution error | 3 | 10 | Andrei | Product owner | 25.11.2017
1 | One person can be logged in at once | 2 | 2 | Andrei | Product owner | 25.11.2017
1 | Logout | 2 | 2 | Andrei | Product owner | 22.11.2017
1 | Refactor database | 4 | 6 | Andrei | Product owner | 23.11.2017
1 | Join as group | 9 | 8 | Ralfs |  | 24.11.2017
2 | burn down chart | 1 | 1 | Ralfs |  | 22.11.2017
2 | Updating end expanding existing UI | 1 | 2 | Ralfs |  | 23.11.2017
1 | Join group | 1 | 1 | Hannes | Scrum master | 23.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
1 | Leave group | 1 | 1 | Hannes | Scrum master | 23.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
1 | Create group | 1 | 1 | Hannes | Scrum master | 22.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
1 | Read group | 1 | 1 | Hannes | Scrum master | 22.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
1 | Update group | 1 | 1 | Hannes | Scrum master | 22.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
1 | Delete group | 1 | 1 | Hannes | Scrum master | 22.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Exception handling | 5 | 3 | Andrei |  | 25.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Exception handling | 4 | 3 | Ralfs |  | 25.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Exception handling | 4 | 4 | Stoycho |  | 25.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Exception handling | 2 | 1 | Hannes |  | 23.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Report planing | 18 | 24 | All of us together |  |  | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Spreading tasks | 8 | 8 | All of us together |  | 22.11.2017 | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it! | fix it!
2 | Chat users updated if user info changed | 1 | 1 | Ralfs |  | 22.11.2017
2 | Show if someone is writing | 1 | 1 | Ralfs |  | 22.11.2017
2 | Show online persons | 2 | 2 | Ralfs |  | 23.11.2017
2 | Show newest chat info | 3 | 2 | Ralfs |  | 23.11.2017

## Sprint 3
Priority | Work | time-est. | time-act. | Person | Role | Date | time-est. | time-act. | Date
2 | WCF hosting | 2 | 3 | Andrei | Scrum master |  | 119 | 126 | 28.11.2017
1 | Splitting report tasks | 5 | 4 | Andrei | Scrum master | 28.11.2017 | 102 | 111 | 29.11.2017
1 | Fix update profile | 2 | 2 | Andrei | Scrum master | 29.11.2017 | 85 | 102 | 30.11.2017
2 | Database Architecture | 4 | 3 | Andrei | Scrum master | 30.11.2017 | 68 | 86 | 1.12.2017
2 | Epilogue | 3 | 2 | Andrei | Scrum master | 1.12.2017 | 51 | 63 | 2.12.2017
1 | Fix music player | 1 | 2 | Stoycho | Product owner | 29.11.2017 | 34 | 56 | 3.12.2017
1 | Optimize transactions | 1 | 1 | Stoycho | Product owner | 29.11.2017 | 17 | 49 | 4.12.2017
2 | Introduction | 2 | 2 | Stoycho | Product owner | 30.11.2017 | 0 | 41 | 5.12.2017
2 | Development Method of Choice | 3 | 3 | Stoycho | Product owner | 4.12.2017
2 | Preliminary Study | 2 | 3 | Stoycho | Product owner | 3.12.2017
2 | Types of Services | 3 | 3 | Stoycho | Product owner | 2.12.2017
1 | Choice of middleware | 1 | 2 | Stoycho | Product owner | 1.12.2017
1 | Security in program | 4 | 3 | Stoycho | Product owner | 28.11.2017
1 | Performance of project | 5 | 4 | Stoycho | Product owner | 30.11.2017
2 | Dos/Ddos protection | 4 | 4 | Stoycho | Product owner
2 | Plan driven Vs. Agile Development | 3 | 2 | Hannes |  | 28.11.2017
2 | Quality Assurance | 3 | 3 | Hannes |  | 1.12.2017
2 | Quality Criteria and Architecture | 2 | 2 | Hannes |  | 29.11.2017
2 | Dedicated Client explanation | 2 | 4 | Hannes |  | 30.11.2017
2 | Web Client explanation | 3 | 4 | Hannes |  | 2.12.2017
3 | Interesting bits of code | 2 | 1 | Hannes |  | 3.12.2017
1 | Signlr spike | 5 | 6 | Ralfs |  | 28.11.2017
1 | test/optimize code | 4 | 3 | Ralfs |  | 30.11.2017
1 | Optimize transactions | 2 | 2 | Ralfs |  | 29.11.2017
2 | Sprint summup | 4 | 5 | Ralfs |  | 4.12.2017
2 | Concurrency in project | 4 | 3 | Ralfs |  | 1.12.2017
2 | Service’s Architecture | 3 | 3 | Ralfs |  | 3.12.2017
1 | MVC application | 30 | 34 | All of us together
1 | MVC spike | 10 | 13 | All of us together |  | 1.12.2017

## Sprint 4
Priority | Work | time-est. | time-act. | Person | Role
| merging Report |  |  | Andrei
| Giving feedback on report |  |  | Andrei
| Requesting edits for report |  |  | Andrei
| Final touches for report |  |  | Andrei