## Backlog
Priority | Name | Time est.
1 | Register
1 | Login
2 | Forgot password
1 | Get profile
1 | Update profile
1 | Delete profile
1 | Multiple chats for one client
1 | Create Chat
1 | Update Chat
1 | Find chat
1 | Delete Chat
1 | Join chat
1 | Leave chat
1 | Send message
1 | Receive Message
1 | Get messages
2 | Show message info
1 | Remove your message
2 | Show if someone is writing
2 | Close chat if its deleted
2 | Show online persons
2 | Show newest chat info
2 | Invite person to chat
2 | Get notification
2 | Remove notifications
1 | Spike on binding
2 | Get songs info
1 | Spike on youtube
1 | Fix problem statement
2 | Choice of method
1 | Plan driven vs agile
1 | Dedicated client
2 | Play song | +
2 | Save song | +
2 | Update song | +
2 | Remove song | +
2 | Create playlist | +
2 | Read playlist | +
3 | Update playlist | +
3 | Delete playlist | +
4 | Sound equalizer | -
4 | Change time displaying | -
3 | Multiplayer game (scalable) | +
2 | Join as group | +
2 | Join group | +
2 | Leave group | +
2 | Create group | +
2 | Read group | +
2 | Update group | +
2 | Delete group | +
3 | Booking | -
2 | Web client | +
3 | News area | -

## Sprint 1
Priority | Work | time-est. | time-act. | Person | Role
1 | Register | 3 | 5 | Andrei | Tester
1 | Login | 2 | 3 | Andrei | Tester
2 | Forgot password | 3 | 3 | Andrei | Tester
1 | Get profile | 3 | 3 | Andrei | Tester
1 | Update profile | 3 | 2 | Andrei | Tester
1 | Delete profile | 2 | 2 | Andrei | Tester
1 | Multiple chats for one client | 2 | 1 | Ralfs | Product owner
1 | Create Chat | 3 | 3 | Ralfs | Product owner
1 | Update Chat | 3 | 3 | Ralfs | Product owner
1 | Find chat | 2 | 2 | Ralfs | Product owner
1 | Delete Chat | 2 | 2 | Ralfs | Product owner
1 | Join chat | 4 | 4 | Ralfs | Product owner
1 | Leave chat | 2 | 2 | Ralfs | Product owner
1 | Send message | 5 | 4 | Ralfs | Product owner
1 | Receive Message | 4 | 4 | Ralfs | Product owner
1 | Get messages | 3 | 3 | Ralfs | Product owner
2 | Show message info | 3 | 2 | Ralfs | Product owner
1 | Remove your message | 2 | 3 | Ralfs | Product owner
2 | Show if someone is writing | 1 | 1 | Ralfs | Product owner
2 | Close chat if its deleted | 2 | 2 | Ralfs | Product owner
2 | Show online persons | 2 | 2 | Ralfs | Product owner
2 | Show newest chat info | 3 | 2 | Ralfs | Product owner
2 | Invite person to chat | 4 | 4 | Ralfs | Product owner
2 | Get notification | 3 | 4 | Ralfs | Product owner
2 | Remove notifications | 2 | 2 | Ralfs | Product owner
1 | Spike on binding | 6 | 5 | Ralfs | Product owner
2 | Get songs info | 4 | 5 | Stoicho | Scrum master
1 | Spike on youtube | 6 | 6 | Stoicho | Scrum master
1 | Fix problem statement | 2 | 2 | Hannes | Documenter
2 | Choice of method | 4 | 4 | Hannes | Documenter
1 | Plan driven vs agile | 3 | 4 | Hannes | Documenter
1 | Dedicated client | 25 | 30 | All of us

## Sprint 2
Priority | Work | time-est. | time-act. | Person | Role
1 | Play song | 1 |  | Stoicho
1 | Save song | 1 |  | Stoicho
1 | Update song | 2 |  | Stoicho
1 | Remove song | 1 |  | Stoicho
1 | Create playlist | 2 |  | Stoicho
1 | Read playlist | 1 |  | Stoicho
2 | Update playlist | 2 |  | Stoicho
2 | Delete playlist | 1 |  | Stoicho
3 | Sound equalizer
3 | Change time displaying
2 | Multiplayer game (scalable) | 6 |  | Andrei | Product owner
1 | Fix database | 1 |  | Andrei | Product owner
1 | Join as group | 1 |  | Hannes | Scrum master
1 | Join group | 1 |  | Hannes | Scrum master
1 | Leave group | 1 |  | Hannes | Scrum master
1 | Create group | 1 |  | Hannes | Scrum master
1 | Read group | 1 |  | Hannes | Scrum master
1 | Update group | 1 |  | Hannes | Scrum master
1 | Delete group | 1 |  | Hannes | Scrum master
3 | Booking
2 | Web client | 30 |  | Each of us
3 | News area
2 | exceptions | 2 |  | Each of us
2 | tests | 20 |  | Each of us
2 | db refactoring | 10 |  | Each of us
2 | burn down chart | 1 |  | Ralfs
2 | Message encryption | 4 |  | Ralfs
2 | Updated person updated in all chats |  |  | Ralfs
chat to activity
no more statu