## Backlog
Priority | Name | Time est.
1 | Register
1 | Login
2 | Forgot password
1 | Create profile
1 | Get profile
1 | Update profile
1 | Delete profile | +
1 | Multiple chats for one client
1 | Create Chat
1 | Update Chat
1 | Find chat
1 | Delete Chat
2 | Invite person to chat | +
1 | Join chat
1 | Leave chat
1 | Send message
1 | Receive Message
1 | Get messages | u
2 | Show message info
1 | Remove your message
2 | Show if someone is writing | +
2 | Close chat if its deleted
2 | Show online persons
2 | Show chat status (online P.)
2 | Show newest chat info
2 | Play song | +
2 | Save song | +
2 | Get songs info
2 | Update song | +
2 | Remove song | +
3 | Change time displaying | u
2 | Notifications | +
3 | Multiplayer game | u
3 | Theme | u
3 | Like | -
3 | Add Friend | -
3 | Remove Friend | -
3 | Manage group | +
1 | Dedicated client
2 | Web client | +
3 | News area | u
3 | Sound equalizer | u
2 | Join as group | +
2 | Booking | +

## Sprint 1
Work | time-est. | time-act. | Person | Role
Get song info from link | 2 |  | Stoicho
Play song | 11 |  |  | Scrum master
Manage song | 8
Connecting user to chat | 12 | 10 | Ralf
User adds user to chat | 10 | 4
Manage chat | 5 | 5 |  | Product owner
Send/Receive message | 3 | 6
UI Template | 10 |  | Hannes
formalities | 8
Little helper (figure out voting) | 12
login | 2 | 3 | Andrei
manage profile | 6 | 3
Friend list | 6
write tests for everything implemented (starting with your own shit) | 16
Per person 30h |  | 2017-11-08