## Backlog
Priority | Name | Time est.
Manage

## Sprint 1
Work | time-est. | time-act. | Person | Role
Get song info from link | 2 |  | Stoicho
Play song | 11 |  |  | Scrum master
Manage song | 8
Connecting user to chat | 12 | 10 | Ralf
User adds user to chat | 10 | 4
Manage chat | 5 | 5 |  | Product owner
Send/Receive message | 3 | 6
UI Template | 10 |  | Hannes
formalities | 8
Little helper (figure out voting) | 12
login | 2 | 3 | Andrei
manage profile | 6 | 3
Friend list | 6
write tests for everything implemented (starting with your own shit) | 16
Per person 30h |  |  | 2017-11-08